## Report
HawkEye - OSINT
Earned Value Analysis Report 30-Day Project Snapshot
| Prepared By: | Jeevan Dhamala
| Date: | 2026-05-05
[42]
| For Period: | Wk 1 = Sprint 1, ... , Wk 5 = Release)
Summary:
Final Earned Value snapshot for the 30-day HawkEye-OSINT project. Cost unit = labor-hours (academic context, no monetary cost). Tracker updated every Friday after the sprint review. Sprints 2 and 4 ran slightly over plan (Intelligence module integration and the 50-post evaluation took longer than estimated); GUI/Release work absorbed minor schedule slip but the team shipped v1.0.0 on Day 30. Final CPI = 0.92 (modest hour overrun); final SPI = 1.00 (on time).
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | TBC | 1 | 2 | 3 | 4 | 5 | Work Package | Planned (TBC) | Actual
1 | Project Initiation | 6 | 6 | 0 | 0 | 0 | 0 | Project Initiation | 6 | 7
2 | Sprint 1 Ingestion Module | 24 | 24 | 0 | 0 | 0 | 0 | Sprint 1 Ingestion Module | 24 | 26
3 | Sprint 2 Search & Scraping Module | 22 | 0 | 22 | 0 | 0 | 0 | Sprint 2 Search & Scraping Module | 22 | 22
4 | Sprint 2 Intelligence Module | 22 | 0 | 22 | 0 | 0 | 0 | Sprint 2 Intelligence Module | 22 | 26
5 | Sprint 3 GUI & Orchestration | 28 | 0 | 0 | 28 | 0 | 0 | Sprint 3 GUI & Orchestration | 28 | 32
6 | Sprint 4 Export, Analysis & Evaluation | 30 | 0 | 0 | 0 | 30 | 0 | Sprint 4 Export, Analysis & Evaluation | 30 | 32
7 | Release & Documentation | 12 | 0 | 0 | 0 | 0 | 12 | Release & Documentation | 12 | 12
0
0
0
0
0
Insert new rows above this one
| Total Budgeted Cost | 144 | 30 | 44 | 28 | 30 | 12
|  | Cumulative Planned Value (PV) | 30 | 74 | 102 | 132 | 144
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 33 | 79 | 113 | 139 | 157
|  | Cumulative Earned Value (EV) | 30 | 69.6 | 102 | 127.5 | 144
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | -3 | -9.4 | -11 | -11.5 | -13
|  | Schedule Variance (SV = EV - PV) | 0 | -4.4 | 0 | -4.5 | 0
|  | Cost Performance Index (CPI = EV/AC) | 0.90909 | 0.88101 | 0.90265 | 0.91727 | 0.9172
|  | Schedule Performance Index (SPI = EV/PV) | 1 | 0.94054 | 1 | 0.96591 | 1
|  | Estimated Cost at Completion (EAC) | 158.4 | 163.4483 | 159.5294 | 156.9882 | 157
Note on A21: Work Breakdown Structure (WBS)
Note on C21: Total Budgeted Cost (TBC)

## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP). | [7 empty] | Earned Value Management Template
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet. | [7 empty] | © 2012 Vertex42 LLC
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5
1 | Project Initiation | 6 | 100% | 100% | 100% | 100% | 100%
2 | Sprint 1 Ingestion Module | 24 | 100% | 100% | 100% | 100% | 100%
3 | Sprint 2 Search & Scraping Module | 22 | 0% | 100% | 100% | 100% | 100%
4 | Sprint 2 Intelligence Module | 22 | 0% | 80% | 100% | 100% | 100%
5 | Sprint 3 GUI & Orchestration | 28 | 0% | 0% | 100% | 100% | 100%
6 | Sprint 4 Export, Analysis & Evaluation | 30 | 0% | 0% | 0% | 85% | 100%
7 | Release & Documentation | 12 | 0% | 0% | 0% | 0% | 100%
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
Insert new rows above this one
|  | Cumulative EV | 30 | 69.6 | 102 | 127.5 | 144

## AC
Actual Cost Worksheet
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period.
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed
WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5
1 | Project Initiation |  | 7 | 0 | 0 | 0 | 0
2 | Sprint 1 Ingestion Module |  | 26 | 0 | 0 | 0 | 0
3 | Sprint 2 Search & Scraping Module |  | 0 | 22 | 0 | 0 | 0
4 | Sprint 2 Intelligence Module |  | 0 | 18 | 8 | 0 | 0
5 | Sprint 3 GUI & Orchestration |  | 0 | 6 | 26 | 0 | 0
6 | Sprint 4 Export, Analysis & Evaluation |  | 0 | 0 | 0 | 26 | 6
7 | Release & Documentation |  | 0 | 0 | 0 | 0 | 12
- | -
- | -
- | -
- | -
- | -
Insert new rows above this one
|  | Total Actual Cost | 33 | 46 | 34 | 26 | 18
|  | Cumulative Actual Cost (AC) | 33 | 79 | 113 | 139 | 157