PROJECT MANAGEMENT PLAN

HawkEye OSINT Analysis Tool

Department of Information Technology and Management

| Document Title | Project Management Plan |
| --- | --- |
| Project Name | HawkEye OSINT Analysis Tool |
| Version | 1.0 |
| Document Date | April 2026 |
| Classification | Academic / Internal Use |
| Methodology | Agile / Scrum, Compressed SDLC |
| Project Duration | 30 Days |
| Team Size | 10 Students |
| License | MIT Open Source |

# Revision History

This section records all revisions to this Project Management Plan following initial baseline approval. Any update to scope, schedule, or deliverables must be reflected here before the revised document is distributed.

| Date | Version | Description of Change | Author |
| --- | --- | --- | --- |
| April 2026 | 1.0 | Initial baseline release for the 30-day sprint. | Project Lead (GUI and Release Team) |

## Document Control

| Document Owner | Project Lead, HawkEye Capstone Team |
| --- | --- |
| Reviewers | Ingestion, Search, Intelligence, and GUI Team Leads |
| Approvers | Course Instructor; Project Sponsor |
| Distribution | Capstone Team; Course Faculty |
| Next Review Date | Day 15 and Day 22 (Integration Reviews) |
| Supersedes | None (initial baseline) |

# Table of Contents

1.  Introduction	1

1.1  Project Overview	1

1.2  Scope Statements	2

1.3  Goals and Objectives	3

1.4  Stakeholders and Key Personnel	3

2.  Project Organization	4

3.  Acquisition Process	5

4.  Monitoring and Control Mechanisms	6

4.1  Earned Value Tracking	6

4.2  Sprint Cadence	6

4.3  Milestone Go / No-Go Gates	6

4.4  Task Tracking	7

5.  Systems Security Plans and Requirements	8

6.  Work Breakdown Structure and Schedule	9

6.1  Work Breakdown Structure	9

6.2  High-Level 30-Day Schedule	11

6.3  Team Assignment by Sprint	11

7.  Project Success Criteria	12

8.  Communication Management Plan	13

8.1  Communication Channels	13

8.2  Meeting Schedule	13

8.3  Working Agreements	14

9.  Risk Management Plan	15

10.  Software Configuration Management Plan	16

11.  Training Plan	17

12.  Quality Assurance Plan	18

12.1 Testing Strategy	18

12.2 Quality Gates	18

13.  Project Measurement Plan	19

13.1 Description	19

13.2 Performance Measurements	19

14.  Reference Materials	20

# Executive Summary

HawkEye is a Python desktop application that helps users verify whether an image shared in a Reddit news post depicts the event it claims to depict. Given a Reddit URL or a direct image-and-claim pair, the tool ingests the post, performs reverse image search, scrapes historical articles, queries the Google Fact Check Tools API, and uses a local AI model to compare the claim against its historical context. The outcome is one of three verdicts: Consistent, Out of Context, or Inconclusive. Each verdict carries a confidence score and the evidence used to produce it.

This Project Management Plan covers the full 30-day development effort carried out by a team of ten students. The project runs on a compressed Agile schedule of four one-week development sprints followed by a two-week integration and quality assurance phase. Work is divided among four sub-teams, each responsible for one layer of the system from end to end. A Project Lead coordinates across sub-teams, owns the schedule, and holds a tiebreaker vote when cross-team decisions reach an impasse.

Key planning elements are captured across fifteen sections. These include the work breakdown structure, team organization, risk register, quality assurance plan, software configuration management policy, communication agreements, and performance measurement framework. The plan is intended as the authoritative baseline against which progress is measured and from which change control decisions are made.

# 1.  Introduction

This Project Management Plan describes the management processes that the HawkEye Capstone Team will follow across the 30-day execution of the HawkEye OSINT Analysis Tool project. The project runs on a compressed Agile schedule divided into four one-week development sprints followed by a two-week integration and quality assurance phase. This document records planning assumptions, team structure, scope decisions, schedule baselines, communication agreements, and risk mitigations. It will be updated as practices change.

## 1.1 Project Overview

HawkEye is an open-source desktop application that helps users determine whether an image shared in a Reddit news post depicts the event it claims to depict. Given a Reddit URL or a direct image-and-claim pair, the tool ingests the post, performs reverse image search, scrapes historical articles, and queries the Google Fact Check Tools API. A local AI model then compares the claim against that historical context and returns one of three verdicts: Consistent, Out of Context, or Inconclusive. Each verdict includes a confidence score and the specific evidence passages the model used to reach it.

The tool is built in Python with a PySide6 desktop interface. It draws on four data sources: Reddit via PRAW, reverse image search via SerpAPI Google Lens with a TinEye fallback, article text via trafilatura and newspaper3k, and structured fact-check records via the Google Fact Check Tools API. Local inference runs through Ollama with Phi-3 3.8B as the default model. All source code is published to GitHub under the MIT license.

## 1.2 Scope Statements

In Scope

- Reddit posts that contain a single primary image in JPEG, PNG, or WebP format.

- English-language source articles only.

- Three-way verdict classification: Consistent, Out of Context, and Inconclusive.

- Local LLM inference via Ollama, with Phi-3 3.8B as the default and Llama 3.1 8B available through the configuration file.

- PDF and JSON report export.

- A six-tab desktop GUI covering Input, Verdict, Timeline, Sources, Raw Evidence, and Logs.

- GDELT DOC API cross-reference for additional historical context.

- Labeled evaluation against the Snopes Fauxtography archive and the MediaEval 2016 corpus.

- Checks whether a webpage existed historically and whether its title/content changed over time. ( Wayback + archive.today )

- Url safety Evaluates whether the domain hosting the article is technically suspicious or linked to malicious infrastructure. ( URLhaus + crt.sh )

Out of Scope

- Deepfake detection and AI-generated image classification.

- Real-time subreddit monitoring or automated crawling.

- Non-English source articles.

- Posts containing multiple images or video content.

- Mobile or web-based deployment.

## 1.3 Goals and Objectives

The project pursues five primary objectives, each mapped to a distinct pipeline stage:

- Ingestion: Accept a Reddit URL or direct image-and-claim pair, then extract the title, body text, subreddit name, top comments, and the image file.

- Image Provenance: Identify prior appearances of the image through reverse image search and perceptual hashing.

- Context Extraction: Scrape original article text, publication date, and source domain from each discovered URL.

- AI Comparison: Pass the Reddit claim and the top scraped contexts to a local LLM. The model returns a structured JSON object with the verdict, a confidence score, and the specific evidence passages it cited.

- Reporting: Render the full analysis in a tabbed GUI and allow the user to export results as a PDF or JSON file.

## 1.4 Stakeholders and Key Personnel

The following stakeholders carry defined responsibilities during the project. Each sub-team lead is accountable for their module from scaffolding through release.

| Role | Team | Responsibilities |
| --- | --- | --- |
| Project Lead | GUI and Release (dual role) | Timeline management, deliverables tracking, final integration, release tag, and README. |
| Ingestion Lead | Ingestion (2 members) | Reddit API, image download, EXIF extraction, perceptual hashing, and SQLite cache. |
| Search and Scraping Lead | Search (3 members) | SerpAPI integration, TinEye fallback, article scraping, and GDELT cross-reference. |
| Intelligence Lead | Intelligence (3 members) | Ollama setup, prompt templates, Fact Check API, verdict logic, and hallucination guard. |
| GUI Lead | GUI and Release (2 members) | PySide6 interface, visualizations, report export, PyInstaller packaging, and GitHub release. |
| Course Instructors | Department Faculty | Rubric evaluation, milestone review, and grading of all seven deliverables. |
| End Users | Journalists, OSINT Analysts, Moderators | Tool validation and feedback during Sprint 4 testing. |

Table 1. Stakeholder roles and primary responsibilities.

# 2.  Project Organization

The team of ten students is divided into four functional sub-teams. Each sub-team owns one layer of the system from end to end. A Project Lead drawn from the GUI and Release team manages the master schedule, tracks deliverables, and resolves cross-team disagreements that the RFC process cannot settle within 48 hours. The four sub-team leads, together with the Project Lead, form the coordination group that owns all cross-team integration points.

| Sub-Team | Size | Members | Ownership |
| --- | --- | --- | --- |
| Ingestion | 2 | Ingestion Lead, Ingestion Dev | Reddit API, image download, EXIF, pHash, SQLite cache, and config.yaml. |
| Search and Scraping | 3 | Search Lead, Search Dev 1, Search Dev 2 | SerpAPI Google Lens, TinEye fallback, trafilatura, newspaper3k, and GDELT cross-reference. |
| Intelligence | 3 | Intelligence Lead, Intel Dev 1, Intel Dev 2 | Ollama and Phi-3, prompt templates, Fact Check API, verdict logic, embedding similarity, and hallucination guard. |
| GUI and Release | 2 | GUI Lead (also Project Lead), GUI Dev | PySide6 interface, timeline chart, report export, PyInstaller packaging, and GitHub release. |

Table 2. Sub-team structure and ownership boundaries.

# 3.  Acquisition Process

This project has no formal procurement process. All third-party services are either open-source, available under a free tier, or covered by a small discretionary team budget reserved for API credits. The acquisition table below records the provenance, access method, and budgetary considerations for each resource in use.

| Resource | Provider | Acquisition Method | Budget Notes |
| --- | --- | --- | --- |
| SerpAPI Google Lens | SerpAPI | Free-tier API key | Credit reserve available for testing. TinEye fallback used if quota is depleted. |
| TinEye Reverse Image Search | TinEye | Free-tier API key | Fallback only. No budget required unless SerpAPI is exhausted. |
| Google Fact Check Tools API | Google | Free API key | No quota concern at capstone scale. |
| Ollama plus Phi-3 3.8B | Ollama / MSFT | Open-source, local install | No cost. Approximately 8 GB RAM required per machine. |
| PRAW (Reddit API) | Reddit / PyPI | Free developer credentials | Standard rate limits apply. SQLite cache prevents repeat calls. |
| PySide6, trafilatura, newspaper3k, and other libraries | PyPI | pip install | No cost. All open-source with pinned versions. |
| GitHub repository | GitHub | Free public repository | No cost under the MIT license. |
| Notion, Trello, Discord | SaaS tools | Free-tier team plans | No cost at team scale. |

Table 3. Acquisition summary for all external resources.

# 4.  Monitoring and Control Mechanisms

Monitoring and control processes keep the project on schedule and within its quality baseline. The Project Lead is responsible for running these processes, escalating when a gate cannot be passed, and updating all tracking artifacts on a fixed weekly cadence.

## 4.1  Earned Value Tracking

The Project Lead maintains an Earned Value tracker in Google Sheets. The sheet records Planned Value, Earned Value, Actual Cost, Schedule Performance Index, and Cost Performance Index for each task. Updates are made every Friday after the sprint review. A final snapshot of the sheet is submitted as Deliverable 3.

## 4.2  Sprint Cadence

Each of the four development sprints follows a consistent weekly rhythm. Sprint planning occurs on Monday morning, when sub-team leads pull items from the backlog and update the Trello board. A mid-sprint standup runs on Wednesday afternoon for fifteen minutes, with blockers logged immediately in the Discord blockers channel. Each sprint closes on Friday with a review session in which sub-teams demonstrate completed work, the Earned Value sheet is updated, and the scope for the following sprint is confirmed.

## 4.3  Milestone Go / No-Go Gates

Nine milestone gates define the critical checkpoints across the 30-day timeline. Each gate carries a binary pass condition and a verification method. Failure at a gate triggers escalation to the full team at the next standup.

| Milestone | Day | Pass Condition | Verification |
| --- | --- | --- | --- |
| Foundation Ready | Day 3 | Repository live; contracts.md merged; all open questions resolved; CI passing; every sub-team branch pushable. | Project Lead demo at Day 3 standup. |
| Ingestion Module Complete | Day 7 | PRAW auth, image download, EXIF, pHash, and SQLite cache all returning real data with unit tests passing. | Ingestion Lead demonstrates three test URLs at Sprint 1 review. |
| Search and Scraping Complete | Day 14 | SerpAPI and TinEye live; article scraper returning text with date and domain for five or more URLs; GDELT integrated. | Search Lead demonstrates at Sprint 2 review. |
| Intelligence Complete | Day 14 | Fact Check API live; LLM returning structured JSON verdict; hallucination guard passing unit tests; embeddings computed. | Intelligence Lead demonstrates three claims at Sprint 2 review. |
| CLI End-to-End | Day 15 | Real Reddit URL produces valid JSON matching the agreed schema for three different posts via CLI. | Project Lead pastes three URLs; all return valid JSON. |
| GUI Integration Complete | Day 21 | All six GUI tabs populated from live pipeline output; no crashes on the standard path. | All ten members test five URLs in the GUI. |
| Export and Analysis Ready | Day 24 | PDF and JSON export functional; 50-post test set run; four analysis charts saved to /docs/charts/. | PDF opens on two machines; results.csv contains 50+ rows. |
| QA Complete | Day 28 | P1 bug count at zero; accuracy and recall metrics measured; median latency below 60 seconds documented. | pytest passing; eval_results.csv committed; latency in Test Document. |
| Final Submission | Day 30 | All seven deliverables in /docs; GitHub v1.0.0 tag live; README links to demo video. | All ten members verify the release page. |

Table 4. Milestone gates with binary pass conditions.

## 4.4  Task Tracking

Every task on the Trello board has an owner, a due day, and a status of To Do, In Progress, or Done. Sub-team leads are responsible for keeping their cards current before each standup. The board is the authoritative record of blocked work, and any task that remains in In Progress for more than 48 hours is flagged for escalation.

# 5.  Systems Security Plans and Requirements

HawkEye runs entirely on the user's local machine. The LLM inference engine (Ollama) never contacts a remote server. Sensitive configuration data is stored only in a gitignored local file. The repository contains a template file with placeholder values so that no credentials are exposed in version control.

No user data, Reddit post content, or scraped article text is transmitted to any cloud service other than the designated third-party APIs: SerpAPI and the Google Fact Check Tools API. The SQLite cache stores results keyed by image perceptual hash and holds no personally identifiable information. All dependencies are pinned to exact versions in requirements.txt to prevent supply-chain drift.

The GitHub main branch is protected. Direct pushes are not permitted. Every change must go through a pull request reviewed by at least one team member from outside the author's sub-team.

This project has no production deployment and no user account system, so a formal Authority to Operate is not required. Any future deployment to a shared server would require an OWASP Top 10 review and dependency vulnerability scanning via pip-audit.

# 6.  Work Breakdown Structure and Schedule

## 6.1 Work Breakdown Structure

The work breakdown structure below decomposes the project into eight major work packages. Each row identifies the owner and the day or day range in which the work is expected to complete.

| WBS | Work Package | Owner | Days |
| --- | --- | --- | --- |
| 1.0 | Project Initiation | Project Lead | Days 1 to 3 |
| 1.1 | Repository setup, branch protection, and CI skeleton | Project Lead | Day 1 |
| 1.2 | contracts.md with pipeline interfaces and JSON schema | All Leads | Days 1 to 2 |
| 1.3 | Open questions resolution and decision log | All Leads | Day 1 |
| 1.4 | Sprint planning; backlog loaded into Trello | Project Lead | Day 2 |
| 2.0 | Sprint 1: Ingestion Module | Ingestion Team | Days 1 to 7 |
| 2.1 | PRAW authentication and Reddit post extraction | Ingestion Lead | Days 1 to 2 |
| 2.2 | Image download, EXIF, and perceptual hash generation | Ingestion Dev | Days 3 to 4 |
| 2.3 | SQLite cache check and direct image-plus-claim input mode | Ingestion Lead | Days 5 to 6 |
| 2.4 | config.yaml centralization; no hardcoded values in any module | Ingestion Lead | Day 7 |
| 2.5 | Unit tests for all ingestion functions | Both Ingestion | Day 7 |
| 3.0 | Sprint 2: Search and Scraping Module | Search Team | Days 8 to 14 |
| 3.1 | SerpAPI Google Lens; SQLite cache keyed by perceptual hash | Search Lead | Days 8 to 9 |
| 3.2 | Article scraper with trafilatura primary and newspaper3k fallback | Search Dev 1 | Days 9 to 11 |
| 3.3 | Rate limiting, retry logic, and TinEye fallback fully wired | Search Lead | Days 11 to 12 |
| 3.4 | GDELT DOC API cross-reference | Search Dev 2 | Days 12 to 13 |
| 3.5 | Unit tests for all search and scraping functions | All Search | Day 14 |
| 4.0 | Sprint 2: Intelligence Module | Intelligence Team | Days 8 to 14 |
| 4.1 | Google Fact Check Tools API with similarity threshold | Intelligence Lead | Days 8 to 9 |
| 4.2 | LLM structured JSON verdict with confidence and evidence | Intel Dev 1 | Days 9 to 11 |
| 4.3 | Hallucination guard: verify cited snippet in scraped text | Intelligence Lead | Days 11 to 12 |
| 4.4 | Embedding similarity via sentence-transformers | Intel Dev 1 | Days 12 to 13 |
| 4.5 | Unit tests for verdict, guard, and embeddings | Intel Dev 2 | Day 14 |
| 5.0 | Sprint 3: GUI and Orchestration | GUI and Project Lead | Days 15 to 21 |
| 5.1 | Orchestrator executing pipeline stages without crashing | Project Lead | Days 15 to 16 |
| 5.2 | PySide6 skeleton with six placeholder tabs | GUI Lead | Day 15 |
| 5.3 | Input tab wired to orchestrator; Verdict tab renders output | GUI Lead | Days 16 to 17 |
| 5.4 | Timeline tab (matplotlib); Sources tab with domain list | GUI Lead | Days 18 to 19 |
| 5.5 | Raw Evidence tab (JSON viewer); Logs tab (live stream) | GUI Lead | Days 19 to 20 |
| 5.6 | Full GUI integration: all tabs from live pipeline output | All Teams | Day 21 |
| 6.0 | Sprint 4: Export, Analysis, and Evaluation | All Teams | Days 22 to 28 |
| 6.1 | PDF export via reportlab | GUI Lead | Days 22 to 23 |
| 6.2 | JSON export: schema-validated result | GUI Dev | Day 23 |
| 6.3 | Run tool against 50 to 100 labeled posts; results.csv | Intel Lead | Days 22 to 24 |
| 6.4 | Analysis charts: reuse-age, domain breakdown, subreddit, topics | Search and Intel | Days 24 to 26 |
| 6.5 | MediaEval 2016 sample; accuracy, precision, recall, confusion matrix | Intel and Search Leads | Days 25 to 26 |
| 6.6 | Failure analysis: categorize incorrect verdicts | Intel Lead | Day 27 |
| 6.7 | Unit tests, cross-team bug bash, and P1 triage | All Teams | Days 26 to 28 |
| 7.0 | Release and Documentation | Project Lead and GUI | Days 29 to 30 |
| 7.1 | README with install, quickstart, and hardware requirements | Project Lead | Day 29 |
| 7.2 | Demo video: two to three minute walkthrough | GUI Lead | Day 29 |
| 7.3 | Written Data Analysis Report with charts | Intel Team | Day 29 |
| 7.4 | Test Document: rubric requirements mapped to test cases | All Teams | Day 29 |
| 7.5 | Cross-platform PyInstaller bundle tested on two or more machines | GUI Lead | Day 29 |
| 7.6 | GitHub v1.0.0 release; all seven deliverables in /docs | Project Lead and GUI | Day 30 |

Table 5. Work breakdown structure (WBS) with ownership and schedule.

## 6.2 High-Level 30-Day Schedule

The schedule below summarizes the exit criteria for each of the five project phases. Passing these criteria is the precondition for moving into the next phase.

| Phase | Duration | Focus | Exit Criteria |
| --- | --- | --- | --- |
| Sprint 1 | Days 1 to 7 | Requirements, Design, and Ingestion | Repo live; contracts.md merged; Ingestion returning real data with unit tests passing. |
| Sprint 2 | Days 8 to 14 | Search, Scraping, and Intelligence | SerpAPI, TinEye, scraper, GDELT, Fact Check API, and LLM verdict all operational. |
| Sprint 3 | Days 15 to 21 | Orchestration and Full GUI Integration | CLI end-to-end by Day 15; all six GUI tabs rendering live data by Day 21. |
| Sprint 4 | Days 22 to 28 | Export, Data Analysis, and QA | PDF and JSON export done; 50-post evaluation; MediaEval run; P1 bugs resolved. |
| Release Phase | Days 29 to 30 | Documentation, Demo, and Submission | README, demo video, and all seven deliverables in /docs; v1.0.0 tag live. |

Table 6. High-level 30-day schedule with phase-level exit criteria.

## 6.3 Team Assignment by Sprint

The matrix below shows the primary focus area for each team member during each sprint. This is not a minute-by-minute schedule; it ensures no team member is blocked waiting on another's output.

| Role | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Release |
| --- | --- | --- | --- | --- | --- |
| Ingestion Lead | PRAW auth and scaffold | Cache and input modes | config.yaml; integration support | Unit tests and bug fixes | Test Document |
| Ingestion Dev | Reddit API and image download | EXIF and pHash | Format validation | Bug fixes | README review |
| Search Lead | SerpAPI scaffold | Lens call and TinEye | Orchestrator build | MediaEval eval; charts | Test Document |
| Search Dev 1 | SQLite cache | Article scraper | Rate limit and retry | NER and topic clusters | Data analysis |
| Search Dev 2 | TinEye stub | trafilatura and GDELT | GDELT parsing polish | Domain charts; MediaEval | Data analysis |
| Intelligence Lead | Ollama and Phi-3 | Fact Check API | Hallucination guard | Embedding scores; test set run | Analysis report |
| Intel Dev 1 | Prompt templates | LLM call and JSON | Verdict logic | sentence-transformers; NER | Analysis report |
| Intel Dev 2 | Hardcoded JSON stub | JSON schema check | Unit tests | Eval automation; confusion matrix | Test Document |
| GUI Lead | PySide6 skeleton | Input tab wiring | Timeline, Sources, Verdict tabs | PDF and JSON export; packaging | Demo video |
| GUI Dev / PM | Repo, CI, contracts | Mock pipeline and smoke test | Orchestrator and full integration | Unit tests; latency measurement | README and release tag |

Table 7. Team assignment matrix by sprint.

# 7.  Project Success Criteria

The project is considered successful when every criterion in the table below is met. These criteria govern both delivery completeness and application quality.

| Criterion | Measure | Target |
| --- | --- | --- |
| All seven deliverables submitted on time | Deliverables checklist complete | By end of Day 30 |
| Application runs end-to-end without crashes | Standard-path test on five real URLs in the GUI | Zero crashes on valid inputs |
| Verdict accuracy | Accuracy on 50 to 100 labeled test posts | 70 percent or above |
| Out-of-Context precision | Precision on Out-of-Context class (sklearn classification report) | 0.65 or above |
| Out-of-Context recall | Recall on Out-of-Context class (sklearn classification report) | 0.60 or above |
| End-to-end latency | Median time from URL submission to verdict across ten posts | Below 60 seconds per post |
| Hallucination guard coverage | Uncited verdicts downgraded to Inconclusive | 100 percent flagged |
| Export functionality | PDF opens on two or more machines; JSON validates against schema | Both functional by Day 24 |
| Open-source release | GitHub v1.0.0 tag live under MIT license with setup guide in README | Verified by all ten members on Day 30 |
| MediaEval generalization accuracy | Accuracy on 200-post MediaEval 2016 sample | 65 percent or above |

Table 8. Project success criteria with target thresholds.

# 8.  Communication Management Plan

Clear communication is critical for a team of ten working asynchronously across a 30-day window. This section defines where decisions happen, when the team meets, and the working agreements that keep the project on track.

## 8.1 Communication Channels

| Channel | Tool | Purpose | Audience |
| --- | --- | --- | --- |
| Weekly Sprint Review | Discord voice or in-person | Friday afternoon: sub-team demos, Earned Value update, next sprint scope. | All 10 |
| Mid-sprint Standup | Discord voice | Wednesday afternoon, 15 minutes; blockers logged in #blockers. | All 10 |
| Sub-team Coordination | Discord per-team channels | Asynchronous technical decisions and code review links. | Sub-team members |
| Blockers Channel | Discord #blockers | Any issue blocking progress; must have an assigned owner by next standup. | Anyone |
| Cross-team RFC | Notion RFC documents | 48-hour comment window; decision locked and logged after window closes. | Relevant leads |
| Meeting Notes | Notion | Sprint notes, decision log, and integration review outcomes. | Project Lead |
| Task Tracking | Trello | Owner, due day, and status per task; updated before each standup. | All 10 |
| Earned Value | Google Sheets | PV, EV, AC, SPI, and CPI per task; updated every Friday. | Project Lead |
| Source Control | GitHub | Protected main; PR with one cross-sub-team reviewer required. | All 10 |

Table 9. Communication channels by purpose and audience.

## 8.2  Meeting Schedule

| Meeting | Cadence | Duration | Participants | Primary Output |
| --- | --- | --- | --- | --- |
| Sprint Planning | Monday of each sprint week | 60 min | All 10 | Backlog assigned; Trello updated. |
| Mid-sprint Standup | Wednesday of each sprint week | 15 min | All 10 | Blockers logged; at-risk tasks flagged. |
| Sprint Review | Friday of each sprint week | 45 min | All 10 | Earned Value updated; demos recorded. |
| Integration Review | Day 15 and Day 22 | 45 min | All leads and Project Lead | Go / no-go decision; scope adjustments. |
| RFC (cross-team) | As needed | Async 48h | Relevant leads | Decision logged; not revisited. |

Table 10. Recurring and ad-hoc meetings.

## 8.3 Working Agreements

The following agreements are adopted by the full team on Day 1 and apply throughout the project. They exist to prevent common team failure modes: decisions made privately, blockers that fester unseen, and code that merges without review.

- No project decisions are made through direct messages. If a decision is not recorded in a channel, it does not count.

- All cross-team decisions follow the RFC process: a short Notion document, a 48-hour comment window, and a locked entry in the decision log.

- The Project Lead holds a tiebreaker vote when an RFC does not reach consensus within 48 hours.

- Branch names use sub-team prefixes: ingestion/, search/, intelligence/, and gui/.

- Commit messages follow the Conventional Commits format: feat:, fix:, docs:, and test:.

- API keys and credentials are never committed to the repository. Only config.example.yaml with placeholder values is tracked.

- Every function that calls an external API must have a corresponding unit test using a mock.

- If a change breaks the main branch, the person who introduced the change is responsible for fixing it before the next standup.

# 9.  Risk Management Plan

Risks are reviewed at every Friday sprint review. Any risk that moves from Medium to High likelihood is posted to Discord #blockers and addressed at the next standup. The Project Lead maintains the risk register and is responsible for escalation.

| Risk | Likelihood | Impact | Mitigation | Fallback |
| --- | --- | --- | --- | --- |
| SerpAPI free-tier quota exhausted during Sprints 2 to 4 | High | High | Cache every result in SQLite keyed by perceptual hash. The same image is never sent to the API twice. | Switch to TinEye API. Small budget reserve covers additional credits if both are exhausted. |
| Phi-3 LLM too slow on team laptops | Medium | High | Default to Phi-3 3.8B. Make the model a config option. Document the 8 GB RAM minimum in the README. | Reduce the top-k articles passed to the LLM from five to three. |
| LLM cites evidence not found in the scraped text | Medium | High | Hallucination guard verifies every cited snippet against the scraped article before accepting the verdict. | Downgrade verdict to Inconclusive with a warning badge in the GUI. |
| Paywalled or JS-heavy sites break the article scraper | High | Medium | Cascade: trafilatura, then newspaper3k, then flag the source as inaccessible without silently dropping. | Inaccessible sources shown with warning badge; analysis continues on available data. |
| Fact Check API returns an irrelevant result | Medium | Medium | Similarity threshold applied before surfacing the fact-check result to the user. | Skip to full LLM pipeline when no high-confidence match is found. |
| Scope additions mid-sprint slow delivery | Medium | High | Scope is locked on Day 1. Change requests go through the RFC process with lead approval. | Descope to the core seven deliverables. Move stretch features to v1.1. |
| Team coordination breaks down over 30 days | Medium | High | Mandatory sprint reviews, blockers channel, RFC process, and clear escalation path to the Project Lead. | Project Lead reassigns blocked tasks. Sub-team lead serves as backup. |
| PyInstaller packaging fails on some OS | Low | Medium | Bundle tested on Day 29, early enough to fix before Day 30. | Ship as Python script with requirements.txt and documented workaround. |
| Labeled test set too small for reliable metrics | Low | Medium | 50 to 100 posts from Snopes and r/worldnews plus 200 MediaEval posts. | Report confidence intervals and note dataset limitations. |
| Ollama or Phi-3 install fails on a team machine | Low | High | All members install Ollama and Phi-3 on Day 1. README documents fallback model options. | Pre-download weights to a shared drive. CI smoke test uses ollama pull phi3. |

Table 11. Risk register with mitigations and fallbacks.

# 10.  Software Configuration Management Plan

All code is version-controlled in a single public GitHub repository. The policies below are enforced from Day 1 and apply throughout the project. They exist to protect code quality, prevent credential leaks, and enforce cross-team knowledge sharing.

| Control | Policy |
| --- | --- |
| Repository | Public GitHub repository under the MIT license. URL created on Day 1 and shared with all ten team members. |
| Branch Protection | The main branch is protected. Direct pushes are not permitted. All changes must be submitted through a pull request. |
| Pull Request Review | Every PR requires at least one approving review from a team member outside the author's sub-team. |
| Branch Naming | ingestion/, search/, intelligence/, and gui/ prefixes by sub-team. |
| Commit Messages | Conventional Commits format: feat:, fix:, docs:, and test:. |
| Credentials | API keys are stored in config.yaml, which is listed in .gitignore. Only config.example.yaml with placeholders is tracked. |
| Tagging and Releases | Final submission is tagged v1.0.0 on Day 30 with a GitHub Release containing readable notes. |
| CI Pipeline | Runs on every push: flake8 linting and unit tests. A failing CI build blocks the PR. |
| Issue Tracking | Trello cards map to GitHub branches and PRs. P1 bugs are tracked as GitHub Issues with linked fix PRs. |
| Sprint Branching | Feature branches open at sprint start and merge via PR at sprint close. No feature branch spans more than one sprint. |

Table 12. Software configuration management controls.

# 11.  Training Plan

The 30-day schedule allows knowledge gaps identified in Sprint 1 to be addressed in Sprint 2 without delaying delivery. The plan below covers technology onboarding and cross-team enablement. If a team member is blocked by unfamiliarity with a required tool, they post in the relevant Discord channel immediately. The sub-team lead is responsible for responding within four hours during working hours. Persistent gaps escalate to the Project Lead.

| Topic | Format | When | Deliverer |
| --- | --- | --- | --- |
| Ollama setup and Phi-3 local inference | 20-minute live walkthrough at Day 1 kickoff | Day 1 | Intelligence Lead |
| SerpAPI Google Lens and quota management | Notion document with annotated code example | Day 1 | Search Lead |
| contracts.md pipeline interface review | Document review at kickoff; leads acknowledge | Day 1 | Project Lead |
| Conventional Commits and PR review process | Covered at Day 1 kickoff; enforced by PR template | Day 1 | Project Lead |
| PySide6 tab and widget patterns | Commented code skeleton committed to the repository | Day 2 | GUI Lead |
| trafilatura and newspaper3k scraping patterns | Notion document with examples for common site types | Day 8 | Search Dev 1 |
| sentence-transformers embedding similarity | Inline code comments in the intelligence module | Day 12 | Intel Dev 1 |
| reportlab PDF generation | Working example committed alongside export module | Day 22 | GUI Lead |
| Sprint retrospective and lessons learned | 30-minute discussion at each sprint review | Fridays | All 10 |

Table 13. Training and knowledge-transfer plan.

# 12.  Quality Assurance Plan

Quality assurance runs in parallel with development from Sprint 2 onward. Unit tests are written alongside each module. Integration smoke tests, labeled evaluation, and cross-team bug bashing occur in Sprints 3 and 4. This section defines the test strategy and the quality gates that govern release.

## 12.1 Testing Strategy

| Test Type | Description | When | Owner |
| --- | --- | --- | --- |
| Unit Tests | pytest unit tests cover core logic. Functions that call external APIs use mocks. | Alongside code in each sprint | Module sub-team |
| CLI Integration Smoke | Orchestrator called with three real Reddit URLs. Output JSON must match the agreed schema. | End of Sprint 3, Day 15 | Project Lead |
| GUI Integration Test | Five real URLs tested in the full GUI. All six tabs must display correct output without crashing. | Day 21 | All ten members |
| Labeled Evaluation | 50 to 100 hand-labeled posts from Snopes and r/worldnews. Accuracy, precision, and recall computed. | Sprint 4, Days 22 to 24 | Intelligence Team |
| MediaEval Benchmark | Approximately 200 posts from MediaEval 2016. Tests generalization beyond Reddit. | Sprint 4, Days 25 to 26 | Intel and Search Leads |
| Cross-team Bug Bash | Each sub-team tests another sub-team's module. Issues triaged in Trello into P1 and P2. | Day 26 | All ten members |
| Latency Measurement | Ten posts timed from URL to verdict. Median recorded in the Test Document. | Day 27 | Project Lead |
| Cross-platform Packaging | PyInstaller bundle tested on two or more machines. | Day 29 | GUI Lead |
| Regression Tests | After P1 fixes, regression test cases are added to prevent recurrence. | Days 27 to 28 | Bug fix owner |

Table 14. Testing strategy by test type and owner.

## 12.2  Quality Gates

- No module merges to main without passing the CI build (linting plus unit tests).

- Every pull request requires one reviewer from outside the author's sub-team.

- All P1 bugs must be resolved before Day 30.

- The hallucination guard must downgrade every verdict that lacks a valid citation to Inconclusive, with no exceptions.

- PDF export must open correctly on at least two machines before the Day 24 milestone is closed.

- Median end-to-end latency must be documented as below 60 seconds before QA is marked complete.

# 13.  Project Measurement Plan

## 13.1 Description

Project measurement covers two areas. Schedule and cost performance are tracked through Earned Value, updated each Friday after the sprint review. Application quality is tracked through evaluation metrics and latency benchmarks collected in Sprint 4. The Project Lead is accountable for collecting and reporting all measurement data. Results appear in Deliverable 3 (Earned Value Sheet) and Deliverable 7 (Test Document).

## 13.2 Performance Measurements

| No. | Measurement | Objective | Metric or Formula | Target |
| --- | --- | --- | --- | --- |
| 1 | Schedule Performance Index | Track schedule health each sprint | EV divided by PV | 0.90 or above at each gate |
| 2 | Cost Performance Index | Track effort efficiency each sprint | EV divided by AC | 0.90 or above at each gate |
| 3 | Verdict Accuracy | Measure correctness against ground truth | Correct verdicts divided by total test posts | 70 percent or above |
| 4 | Out-of-Context Precision | Minimize false positives | TP divided by (TP plus FP) for Out-of-Context class | 0.65 or above |
| 5 | Out-of-Context Recall | Minimize false negatives | TP divided by (TP plus FN) for Out-of-Context class | 0.60 or above |
| 6 | Median End-to-End Latency | Confirm newsroom-scale usability | Median seconds from URL to verdict across ten posts | Below 60 seconds |
| 7 | Hallucination Guard Coverage | Catch all uncited verdicts | Uncited verdicts flagged divided by total uncited | 100 percent |
| 8 | P1 Bug Closure Rate | Track resolution of critical defects | P1 bugs closed divided by P1 bugs opened | 100 percent by Day 28 |
| 9 | API Cache Hit Rate | Reduce redundant API calls in testing | Cache hits divided by total analysis requests | Above 50 percent |
| 10 | Sprint Velocity | Confirm consistent throughput across sprints | Story points completed per sprint | Within 15 percent of Sprint 1 |
| 11 | Deliverables Completion | On-time delivery of course artifacts | Deliverables finished by due day divided by seven | Seven of seven by Day 30 |
| 12 | MediaEval Generalization Accuracy | Verify performance outside Reddit inputs | Accuracy on the 200-post MediaEval sample | 65 percent or above |

Table 15. Performance measurements with formulas and targets.

# 14.  Project Plan Approval

The signatures below confirm that the undersigned have reviewed this Project Management Plan. Each signatory has voiced any applicable concerns to the Project Manager, agrees that the plan accurately reflects the expectations and the conditions required for the project to succeed, is committed to providing the listed resources, and is not aware of any undocumented condition that would prevent successful delivery.

| Review Date | April 2026 |
| --- | --- |
| Project Duration | 30 Days (Day 1 through Day 30) |
| Scribe | Project Lead |
| Baseline Version | 1.0 |

END OF DOCUMENT