## Instructions
RISK MANAGEMENT LOG
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each risk identified, complete the following:
A | ID: A unique ID number used to identify the risk in the risk tracking log.
B | Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
C | Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
D | Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue.
E | Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
F | Risk Description: This column should be populated with a description of the risk.
G | Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
H | Risk Area: This column should be populated with the appropriate risk area.
I | Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
J | Trigger: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
K | Risk Response Strategy: This column should be populated with the preferred risk response strategy.
L | Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
M | Contingency Plan: This column should be populated with a description of the risk contingency plan.
Column | Instructions For Changing the Contents of Drop-Down Menus
C, D, H | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## Risk_Tracking_Log
RISK MANAGEMENT LOG | [7 empty] | RISK MANAGEMENT LOG
Project Name: |  |  | HawkEye Osint |  |  |  |  | Project Name: | HawkEye Osint
Project Manager Name: |  |  | Mark Fedechko |  |  |  |  | Project Manager Name: | Mark Fedechko
Project Description: |  |  | <required> |  |  |  |  | Project Description: | <required>
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
EX. | Open | High | Low | Yellow | EXAMPLE: Current project skill set may not be adequate to complete all project work. The current development team has been working in a Windows 2k environment, and the current requirements are for a LINUX environment. The project schedule would require 1500 development hours of a skilled LINUX operator, and approximately 1900 to 2200 if we retrain our current resources. | EXAMPLE: If required skills are not identified or obtained, project schedule may slip and possibly restrict the accomplishment of project goals. | Project Resources Budget Schedule | EXAMPLE: Schedule approaches the required start date with no identification of required skill sets. | EXAMPLE: Four weeks prior to scheduled start date if no resource is identified with required skill set implement contingency plan. | Mitigation | EXAMPLE: Find internal resource that meets required skill set or train existing resources on LINUX. | EXAMPLE: Find resource that meets required skill set through external hiring sources.
1 | Closed | High | Low | Closed | Delayed implementation of the GUI | The project would be unusable without a functional GUI. | Overall Project Failure | Gui Features fail during testing and user interaction | GUI milestones are missed or interface errors remain unresolved | Mitigation | Assign additional frontend devlopers and increase GUI testing frequency | revert to a simplified GUI that keeps core functionality
2 | Closed | High | Low | Closed | Failure to implemment the API for reading reddit | The project would be unusable without the read only reddit API | Overall Project Failure | Reddit data cannot be retrieved or displayed correctly | API requests fail repeatedly or reddit changes API Permissions | Contingency | Implement API Monitoring and create backup retrival methods | switch to alternative OSINT data sources or use manuel imports
3 | Open | Medium | Medium | Yellow | Limitations in reverse image search tools returning imprecise or irrelevent results | This will provide the user with incorrect information and result in a inconcistent experiance. | Surety Considerations | search results return unrelated or incomplete matches | Reverse image tool accuray drops below acceptable levels | Acceptance | cross-refrence results using multiple image search engines | notify users of reduced confidence and limit unsupporeted conclusions
4 | Open | High | Medium | Red | Failure of article scraping on paywalled or java script heavy websites | This will not provide information for the LLM to process, causing a disruption in the workflow. | Data/Information | article scraping failes or pages return errors | websites implement anti-bot protection or java script rendering changes | Contingency | use alternative scraping libraries and rotating user agents | replace failed sources with alternative news or article providers
5 | Open | Low | Low | Green | Reduced local LLM performance on lower-spec hardware | The time taken to process requests will simply be too long. | Reliability of Systems | long response times or delayed processing | hardware exceeds safe limits during testing | Transfer | optimize code and reduce unnecessary processing tasks | move processing tasks to high spec hardware or cloud systems
6 | Open | Medium | Low | Green | Bugs in GUI or Report export functionality | This will affect the end users understanding of the LLM's output. | Surety Considerations | users are unable to export reports or view interface properly | UI errors appear during demonstrations or testing | Mitigation | conduct regular UI testing and bug fixing sessions | provide manual reporting methods until functionality is restored
7 | Open | Medium | High | Red | Database/cache corruption | This will prevent the LLM of reaching accurate conclusions. | Reliability of Systems | missing or corrupted stored data appears during testing | database save or retrieval errors occur | Acceptance | implement automatic backups and verify validation checks | restore previous database backups and isolate corrupted records
8 | Open | High | Low | Yellow | Loss of image EXIF metadata | Lossing EXIF metadata will give inaccurate results or no results for the end user to look at, rendering the tool as ineffective in it's goal. | Reliability of Systems | metadata fields appear blank or incomplete | uploaded images contain stripped or unsupported exif data | Contingency | validate image metadata before processing | inform users that metadata analysis is unavaliable for affected files
11 | Open | Medium | Low | Green | Limited development time reducing the scope of testing and documentation | This will allow for bugs and errors to maintain in the project without being found or fixed | Future Procurements | increased number of unresolved bugs or documentation gaps | development deadlines reduce avaliable testing time | Acceptance | prioritize core testing tasks and maintain minimum documentation standards | delay any nonessential features until testing and documentation are complete
12 | Open | Medium | Medium | Yellow | Reddit posts not containing a usable image | This will leave the LLM without a image to inspect when looking at posts, limiting the posts that will get looked at, potentially resulting in a lower scope of search. | Surety Considerations | reddit posts lack usable images | retrieved posts fail image validation checks | Avoidance | filter posts before analysis and prioritize image-based content | expand to searches to aditional subreddits or external image sources
13 | Open | Medium | Medium | Yellow | Reverse image searches returning few or unrelated results | This will result in a weak conclussion for the user. | Surety Considerations | search results provide few meaningful image matches | reverse image searches return mostly unrelated content | Contingency | use multiple search providers and improve search filtering | reduce reliance on reverse image search conclussions
14 | Open | High | Low | Yellow | scrapped articles may contain firewalls or heavy javascript rendering or minimal content | This will prevent the LLM of gaining a holistic view of every image they could possibly look at. This can cause potential links of articles and photos being missed. | Data/Information | scrapped article content appears incomplete or inaccessable | firewalls or dynamic webpage content block scrapping requests | Avoidance | use browser automation and alternative extraction tools | manually review blocked articles or use alternative news sites
15 | Open | High | Low | Yellow | Image EXIF metadata may be stripped by the hosting platform before the image is downloaded. | This will interupt the work flow of the program and result in | Data/Information | metadata information disapears after image download | hosting websits compress or modify uploaded files | Contingency | collect images from original upload sources whenever possible | notify users of unavaliable metadata and continue limited analysis
16 | Open | High | Medium | Red | Hallucination or overconfident classification of a post | Provides inacurate results for the user | Surety Considerations | the model incorrectly identifies or classifies content | edge cases or biased training data create inconsistent outputs | Mitigation | add verification checks and improve classification training data | require manual review for uncertain classifications
17 | Open | High | Low | Yellow | Incorrect verdicts on edge cases | Provides inacurate results for the user | Surety Considerations | incorrect conclusions appear in unusual or edge-case scenarios | inputs fall outside expected operating conditions | Mitigation | expand testing datasets and implement confidence scoring | flag low-confidence results for manual analysis
18 | Open | Medium | Low | Green | Members not communicating or engaging within the discord | This will result in a rush to complete the project or lacking features in the end project. | Organizational/Change Management | team members miss meetings or fail to complete tasks | reduced discord activity or delayed responses from members | Mitigation | establish weekly check-ins and enforce communication standards | reassign tasks to active team members when neccesary
19 | Open | Medium | Low | Green | Delaying team meetings | This will induce an inorganized team, disrupting work flow and a buggier end product | Organizational/Change Management | development milesstone begin falling behind schedule | consecutive deadlines are missed or delayed | Mitigation | use progress tracking and redistribute workloads | reduce project scope to preserve core deliverables
20 | Open | High | Medium | Red | Delayed reverse image search integration | This will be a missing end function. | Data/Information | reverse image search functionality remains unfinished | integration testing repeatedly fails | Mitigation | allocate additional development time and debugging resources | temporarily release the application without reverse image functionality
21 | Open | Low | Medium | #REF! | Duplicated work because of miscordination | This will result in overall wasted individual team member time and or confusing information resulting in more wasted time. | Schedule | duplicate code or repeated tasks appear in development | team members working on overlapping assignments without cordination | Avoidance | improve task tracking and require frequent project updates | conduct code reviews and reorganize devolopment assigments
22 | Open | High | Medium | Red | Merge conflicts from sub-teams working on the github repository | This will result in a buggier end produt because of confusion in workflow. | Organizational/Change Management | frequent merge conflicts delat repository updates | multiple developers modify the same files simultaniously | Avoidance | enfore branch management and pull request reviews | roll back conflicting changes and manually merga stable versions
`
Note on A5: • ID: A unique ID number used to identify the risk in the risk management log.
Note on B5: • Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
Note on C5: • Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
Note on D5: • Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue. o High: Greater than 70% probability of occurrence. o Medium: Between 30% and 70% probability of occurrence. o Low: Below 30% probability of occurrence.
Note on E5: • Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
Note on F5: • Risk Description: This column should be populated with a description of the risk.
Note on G5: • Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
Note on H5: • Risk Area: This column should be populated with the appropriate risk area.
Note on I5: • Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
Note on J5: • Triggers: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
Note on K5: Risk Response Strategy: This column should be populated with the preferred risk response strategy.
Note on L5: • ResponseStrategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
Note on M5: • Contingency Plan: This column should be populated with a description of the risk contingency plan.

## DropDown_Elements (hidden)
Risk Area
Schedule
Initial Costs
Life-cycle Costs
Technical Obsolescence
Feasibility
Reliability of Systems
Dependencies/Interoperability
Surety Considerations
Future Procurements
Project Management
Overall Project Failure
Organizational/Change Management
Business
Data/Information
Technology
Strategic
Security
Privacy
Project Resources